## Team 1_Project 6_Daily Tracker
Task No | Description | Task Assigned to | Status | Start Date | End Date | Estimate Effort Required | Actual Effort
1 | Requirement Analysis(Input and Output Devices) | Anchal | Completed | 2025-05-10 | 2025-05-10 | 7Hrs | 7Hrs
2 | Requirement Analysis(Input and Output Devices) | Anchal | Completed | 2025-06-10 | 2025-06-10 | 7 Hrs | 7Hrs
3 | Requirement Analysis(Software) | Viswajeet, Anchal | Completed | 2025-06-10 | 2025-06-10 | 7 Hrs | 7Hrs
4 | Requirement Analysis(Software) | Anchal | Completed | 2025-06-10 | 2025-06-10 | 7 Hrs | 7Hrs
5 | Task creation - Github | Ruben | Completed | 2025-06-10 | 2025-06-10 | 7 Hrs | 7Hrs
6 | Hardware Architecture - I Sensors | Viswajeet | Completed | 2025-06-10 | 2025-06-10 | 7Hrs | 7Hrs
7 | Hardware Architecture - I Sensors | Surya | Completed | 2025-06-10 | 2025-06-10 | 7Hrs | 7Hrs
8 | Software Architecture-I Sensors | Viswajeet | Completed | 2025-06-10 | 2025-06-10 | 7Hrs | 7Hrs
9 | Software Architecture-I Sensors | Ruben, Viswajeet | Completed | 2025-06-10 | 2025-06-10 | 7Hrs | 7Hrs
10 | Circuit Design-I | Surya | Completed | 2025-06-10 | 2025-06-10 | 7Hrs | 7Hrs
11 | Hardware Architecture | Viswajeet | Completed | 2025-07-10 | 2025-07-10 | 7Hrs | 7Hrs
12 | Hardware Architecture-I | Viswajeet, Surya | Completed | 2025-07-10 | 2025-07-10 | 7Hrs | 7Hrs
13 | Software Architecture-I | Surya | Completed | 2025-07-10 | 2025-07-10 | 7Hrs | 7Hrs
14 | Software Architecture-I | Viswajeet | Completed | 2025-07-10 | 2025-07-10 | 7Hrs | 7Hrs
15 | Circuit Design-I | Ruben, Viswajeet | Completed | 2025-07-10 | 2025-07-10 | 7Hrs | 7Hrs
16 | Hardware Architecture-II | Viswajeet, Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
17 | Hardware Architecture-II | Viswajeet | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
18 | Software Architecture-II | Viswajeet, Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
19 | Software Architecture-II | Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
20 | Circuit Design-II | Viswajeet | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
21 | Hardware Architecture-III | Ruben, Viswajeet | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
22 | Hardware Architecture-III | Viswajeet, Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
23 | Software Architecture-III | Viswajeet | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
24 | Software Architecture-III | Viswajeet, Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
25 | Circuit Design-III | Surya | Completed | 2025-08-10 | 2025-08-10 | 7Hrs | 7Hrs
26 | Hardware Setup (FlowChart) | Viswajeet | Completed | 2025-09-10 | 2025-09-10 | 7Hrs | 7Hrs
27 | Hardware Setup (FlowChart) | Ruben, Viswajeet | Completed | 2025-09-10 | 2025-09-10 | 7Hrs | 7Hrs
28 | Hardware Setup (Code) | Viswajeet, Ruben | Completed | 2025-09-10 | 2025-09-10 | 7Hrs | 7Hrs
29 | Hardware Setup (Code) | Viswajeet | Completed | 2025-09-10 | 2025-09-10 | 7Hrs | 7Hrs
30 | Hardware Setup (State Machine Diagram) | Viswajeet, Surya | Completed | 2025-09-10 | 2025-09-10 | 7Hrs | 7Hrs
31 | Development & Integration(Coding) | Ruben | Completed | 2025-10-10 | 2025-10-10 | 7Hrs | 7Hrs
32 | Development & Integration(Integration) | Ruben | Completed | 2025-10-10 | 2025-10-10 | 7Hrs | 7Hrs
33+H38A34:I38 | Development & Integration(Unit Testing) | Ruben | Completed | 2025-10-10 | 2025-10-10 | 7Hrs | 7Hrs
34 | Development & Integration(coding) | Ruben | Completed | 2025-10-10 | 2025-10-10 | 7Hrs | 7Hrs
35 | Development & Integration(Integration) | Ruben | Completed | 2025-10-10 | 2025-10-10 | 7Hrs | 7Hrs
36 | Development & Integration(Integration) | Ruben | Completed | 2025-11-10 | 2025-11-10 | 7Hrs | 7Hrs
37 | Development & Integration(Coding) | Ruben | Completed | 2025-11-10 | 2025-11-10 | 7Hrs | 7Hrs
38 | Development & Integration(Coding) | Ruben | Completed | 2025-11-10 | 2025-11-10 | 7Hrs | 7Hrs
39 | Development & Integration(Unit Testing ) | Ruben | Completed | 2025-11-10 | 2025-11-10 | 7Hrs | 7Hrs
40 | Development & Integration(Integration) | Ruben | Completed | 2025-11-10 | 2025-11-10 | 7Hrs | 7Hrs
41 | Development & Integration(Coding) | Ruben | Completed | 2025-12-10 | 2025-12-10 | 7Hrs | 7Hrs
42 | Development & Integration(Integration) | Ruben | Completed | 2025-12-10 | 2025-12-10 | 7Hrs | 7Hrs
43 | Development & Integration(Integration) | Ruben | Completed | 2025-12-10 | 2025-12-10 | 7Hrs | 7Hrs
44 | Development & Integration(Coding) | Ruben | Completed | 2025-12-10 | 2025-12-10 | 7Hrs | 7Hrs
45 | Functional Testing | Ruben | Completed | 14/10/2025 | 14/10/2025 | 7Hrs | 7Hrs
46 | Debugging | Ruben | Completed | 14/10/2025 | 14/10/2025 | 7Hrs | 7Hrs
47 | Debugging | Ruben | Completed | 14/10/2025 | 14/10/2025 | 7Hrs | 7Hrs
48 | BugFixing | Ruben | Completed | 14/10/2025 | 14/10/2025 | 7Hrs | 7Hrs
49 | Functional Testing | Ruben | Completed | 14/10/2025 | 14/10/2025 | 7Hrs | 7Hrs
50 | Documentation(Presentation) | Anchal | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs
51 | Functional Testing | Ruben | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs
52 | Debugging | Ruben | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs
53 | BugFixing | Ruben | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs
54 | Documentation(Project Report) | Anchal | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs
55 | Documentation(Presentation) | Anchal | Completed | 15/10/2025 | 15/10/2025 | 7Hrs | 7Hrs